## Slide 1: Principles of Purchasing Week 8 Planning in Purchasing operation Lecturer: Samson Ndonye

## Slide 2: Lecture Learning outcomes
At the end of the lecture, you will be able to:
1. Explain the key terms used in procurement planning
2. Understand the role of procurement planning in the procurement cycle
3. Describe the type of procurement plan and the contents of procurement plan.

## Slide 3: Introduction
A procurement plan is a budget implementation instrument used to record all the forecasted requirements for goods, services, and works of all the departments of an organization
It is an integral part of the budgeting process as the financial estimates are derived from cost estimates of individual items in the procurement plan
A procurement plan enables the execution of an approved budget and ensures cost savings, efficient business operations and increased value for money

## Slide 4: Definitions of Key Terms in Procurement Planning

## Slide 5: Procurement planning
It is the process of deciding what to buy, when to buy and from what source
It is the primary function that determines and guides the subsequent purchasing activities of the organization for the specified duration of the plan
The procurement planning is then summarized in the document known as the Procurement Plan

## Slide 6: Aggregation and Consolidation
This is the process of combining all the requirements with similar specifications and attributes in the procurement plan to enjoy economies of large-scale buying.

## Slide 7: Considerations during aggregation and consolidation
The needs of similar nature and are likely to attract potential bidders
The period of aggregation –whether aggregation should be done for a whole year or whether the seasonal price fluctuations require the aggregates be limited to particular seasons as is expected for primary food commodities
Whether storage and distribution capacity and costs offset any potential economies of scale cost savings achieved through aggregation
The optimum size and type of contract to attract the greatest, most responsive competition, taking into account the market structures for the items required
The need to apply any applicable measures to promote the participation of small enterprises, end-user or community participation

## Slide 8: Considerations during aggregation and consolidation
Items will be subjected to the same bidding requirements and conditions of the contract; and
The potential to realize savings in time or transaction costs or facilitate contract administration by the buying organization

## Slide 9: Advantages of aggregation and Consolidation
Increases the bargaining power of a buying organization
May attract quantity discounts-aggregation may afford the buyer quantity discounts as needs of the same specifications are consolidated into one order

## Slide 10: Advantages of aggregation and Consolidation
Low ordering costs, i.e., the costs of placing orders may come down considerably due to consolidation
Elevates the buyer position from the perspective of the supplier, the buyer becomes an important customer to the supplier due to large orders
Consolidation and aggregation can lead to the application of a more competitive procurement method that could save money to a buying organization

## Slide 11: Lotting
This refers to dividing procurement requirements into separate contracts that would otherwise be procured in a single contract
This is done with the realization that the award of a separate contract may result in the best value for a buying organization
Lotting may also be as a result of an attempt to comply with the preference and reservation scheme to ensure that certain lots are reserved for the target groups in the procurement budget

## Slide 12: When to apply lotting in the procurement plan
When unbundling the contracts for purposes of preferences and reservation schemes
When the award of several separate contracts will result in the best overall value for the buying entity by applying a competitive procurement method
Where lotting is meant to cater for small enterprises that would not qualify for a complete package in a single contract
When the division into separate lots is likely to attract more suppliers enabling the participation of bidders who are able to bid for some, but not all types of items

## Slide 13: Circumstances under which lotting is not permissible
For purposes of avoiding the established procurement thresholds
Where the award of separate contracts will create problems of compatibility, standardization or interchangeability between separate lots
Where the award of separate contracts would invalidate or restrict any contractors warranty or liability of already existing contract; and
Where the award of several separate contracts would increase the cost of servicing, maintenance or similar requirements

## Slide 14: Grouping
This refers to separating procurement needs into an appropriate classification of goods, works, services, and consultancies
The grouping may also consider the cost of the items, the complexity of the market and the importance of the item to the buying organization
As a general rule, these should not be mixed in procurement except in special cases where they are inseparable, considering the cost and difficulty in the procurement of each item

## Slide 15: Packaging
This refers to putting together the requirements in a single purchase order known as a procurement package
Putting items into a single procurement package means the items are to be purchased together either in a single bid or request for quotation
Packaging assists the procurement function in choosing the appropriate procurement method to use, among other considerations

## Slide 16: Packaging
  Important forms of procurement packaging are as follows
  The grouping of procurement requirements within a procurement category for the purpose of acquiring them under a single contract
  The division of one requirement into multiple lots, where bidders can submit bids for one, several or all lots ; and
  Grouping of procurement requirement, e.g., where the need for equipment involve installation and extends to training of the operators, which would call for tender for the supply, installation, and training as a package
  Whether there are suppliers that can provide a combination of procurement categories as may be required in the case of supply, installation, and training

## Slide 17: Packaging
Packaging assists the procurement function in choosing the appropriate procurement method to use, among other considerations
  The ability of the procurement unit to coordinate suppliers
  The possibility of local suppliers being able to fulfill the requirement in a procurement package and whether such packages may limit their participation
  Whether the requirements are needed simultaneously
  Identical items
  Item sizes-large or small items; and
  Cost of the items

## Slide 18: Importance of procurement planning:
It allows planners to determine if expectations are realistic; particularly the expectations of the requesting entities, which usually expect their requirements met on short notice and over a shorter period than the application of the corresponding procurement method allows
It is an opportunity for all stakeholders involved in the processes to meet in order to discuss particular procurement requirements
It permits the creation of a procurement strategy for procuring each requirement that will be included in the procurement plan
Planners can estimate the time required to complete the procurement process and award contract for each requirement

## Slide 19: Importance of procurement planning
The need for technical expertise to develop technical specifications and/or scope of work for certain requirements can be assessed, especially where in-house technical capacity is not available or is non-existent
Planners can assess the feasibility of combining or dividing procurement requirements into different contract packages
The procurement plan is the product of the procurement planning process
It helps to decide what to buy, when and from what sources, i.e., it defines the need, the method of procurement and when the procurement process will be initiated

## Slide 20: TYPES OF PROCUREMENT PLANS

## Slide 21: 1. Individual procurement plan
Refers to the creation of a procurement plan for each individual procurement item/requirement
Once the need has been identified and the requisition raised, and approval obtained for the purchase of a requirement, the procurement unit may proceed to develop individual procurement plan for the purchase of the item
The procurement unit may develop individual procurement plans due to the requirement's strategic or complex nature to allow for the isolation and management of extremely high risk and a high-cost requirements under a project procurement

## Slide 22: Contents of individual procurement plan
A description of the requirement, including the schedule required for delivery, implementation or completion of the goods, works, services or consultancy
The estimated value of the requirement
The proposed procurement method
A justification for the use of any method other than open tendering
An estimate of the time required for each stage in the procurement cycle
The proposed type of contract; and
An indication of the resources required and available for management of the procurement process and contract administration

## Slide 23: 2. Departmental Procurement Plans
This contains the details of procurement requirements and activities of the concerned department for the planned period
The procurement needs of each department are then summarized into departmental procurement plans
Some procurement needs cannot be anticipated, and the plans can therefore never be accurate

## Slide 24: 3. Consolidated Procurement Plans
All the procurement needs of all the departments of an organization can be aggregated in corporate procurement plan known as the consolidated procurement plan.
The procurement unit plays the lead role in initiating the procurement planning process by engaging the user departments to list their requirements approved by departmental heads.

## Slide 25: 3. Consolidated Procurement Plans-The information collected would include:
The expected requirement for goods/services/works
Quantities/ volume of requirements
The delivery schedule for the identified requirements
Estimated cost/ budget

## Slide 26: Contents of a Procurement Plan
A detailed description and breakdown of goods, services, works and consultancies required to carry out activities of the buying unit
A schedule of planned delivery, implementation or completion dates for all goods, works, services, and consultancies required taking into account the necessary time for effecting the proceedings

## Slide 27: Contents of a Procurement Plan
An indication and justification for whether a procurement requirement should be procured under single-year period or multi-year arrangement
An indication of which items should be aggregated for procurement as a single package or procurement through any applicable arrangements for common use items
Where aggregation is justified, the optimal period for such an aggregation should be indicated taking into account seasonal price variations, warehousing and distribution capacity and product shelf life
An indication of all items divided into lots
An estimate of the value of each package of goods, works, services and consulting, the design required, an indication of the budget and the possible sources of funding

## Slide 28: Contents of a Procurement Plan
An indication of rules applicable to procurement: for instance, specific rules dictated by an international agreement in the case of donor-funded procurement
An indication of the anticipated procurement method for each procurement requirement, including the need for pre-qualification, the anticipated time to complete a procurement cycle taking into account the applicable approval requirements
An indication of whether the procurement function will be carried out by the procuring entity, a specialized procurement unit, any other special agency designated to procure common-use items or any other body
An indication of the warehouse requirements for storing the planned procurement

## Slide 29: Contents of a Procurement Plan
An indication of the shelf life of any goods that may be perishable or degradable

## Slide 30: Conclusion
In conclusion, procurement planning plays a vital role in the efficient execution of an organization's budget, ensuring value for money and optimizing resource allocation
By consolidating, lotting, grouping, and packaging procurement needs, organizations can benefit from economies of scale, enhance competition, and streamline operations
Effective procurement planning also mitigates risks by promoting transparency and accountability throughout the procurement cycle

## Slide 31: Review Questions
Explain
Explain the importance of a procurement plan to an organization
Identify
Identify the key contents of a procurement plan
Discuss
Discuss the factors that a procurement unit should consider during aggregation of procurement requirements
Explain
Explain the advantages of aggregation and consolidation
Discuss
Discuss the various types of procurement plans
Describe
Describe the specific tasks involved in the procurement planning process

## Slide 32
END